| Meeting Date/Time: 10/12/25 6:30 pm | Meeting Location: Zoom |
| --- | --- |

| Attendees |  |  |  |
| --- | --- | --- | --- |
| Nadia Eslinger, Melinda Peer, Crystal Williams Jessica McAfee, Latriana Robertson, Hannah Chavis, Ebony Crutchfield-Wiley, Keneasha ScottAngela Austin |  |  |  |

| Agenda Items |  |
| --- | --- |
| Venue Recommendations | Budget |
| Vendor Recommendations | Calendar |
| Budget | Subcommittees |

#### Call to Order & Meditation - 6:30 pm by Soror Eslinger

#### Recommendations for Venue

The committee reviewed different venue options and discussed needs for the event. Sorors McAffee, Peer, and Eslinger will continue to search for a venue and hope to secure something by the end of the year.

#### Recommendations for Other Vendors were discussed and a list was compiled for the following services:

  - Caterers

  - Bartenders

  - DJ

  - Performers/Live Band

  - Host/MC

  - Design/Decor

#### Budget

  - Anticipated Cost- $28,000

  - Anticipated Revenue - $20,000

  - Cost to the Chapter - $8,000

#### Calendar

  - January - March 30/30 Campaign (partner with Fundraising)

  - November - Event

  - November 9th - Service Event

    - Quilts - One preserved for the chapter and one auctioned and money donated to Lupus Foundation of Arkansas

    - Community Service Project - actual hands in dirt type of situation

      - Food Bank

      - Little Rock Watershed

#### Subcommittees

##### A. Logistics, Registration & Guest Services

##### -Finance Team

##### Lead: Keneasha Scott

##### Committee Members - Crystal, Brandis
B. Program & Entertainment

Lead: Nadia Eslinger

Committee Members: Crystal

##### C. Venue, Decor & Atmosphere

Lead: Jessica Willis

Committee Members: Kay Arnold

##### D. Food & Beverage

Lead: Melinda

Committee Members: Angela Austin

##### E. Marketing & Communications

- Public Relations

Lead: Alyssa Robinson

##### F. Sponsorships & Fundraising

-Finance Team

Lead:

##### G. History & Legacy

- Heritage & Archives

Leads: Jannice Haynes & Edith Ewings

##### H. Gifts, Awards & Special Guest Services

- Membership

Lead: Ebony Crutchfield- Wiley

Next meeting - November 9th at 6:30 pm

Recommendations to Executive Board to be presented to Chapter

Item

None